OrangeHRM Version 5.0
Test Plan

Project: OrangeHRM
Version: 1.0
Prepared By: QA Team
Date: 2026-04-18
Review Status: Baselined

## Revision History

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 0.1 | 2026-04-18 | QA Team | Initial Draft |
| 1.0 | 2026-04-18 | QA Lead | Reviewed & Baselined |
| 2.0 | 2026-04-18 | QA Lead | Enhanced — Communication Plan, Metrics, Closure Criteria, Regression Strategy, Assumptions, Dependencies, Effort Estimates added |

## Approvals

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
|  | QA Lead |  |  |
|  | Project Manager |  |  |
|  | Business Analyst |  |  |
|  | Technical Lead |  |  |
|  | Product Owner |  |  |

## Table of Contents

Introduction

Project Overview

Test Objectives

Scope of Testing

Assumptions

Dependencies

Test Strategy

Test Levels & Types

Entry & Exit Criteria

Test Closure Criteria

Test Metrics & KPIs

Communication Plan

Test Environment

Test Data Requirements

Test Deliverables

Defect Management

Risk & Mitigation Plan

Resource Plan

Test Schedule & Milestones

Requirements Traceability Matrix (RTM)

Appendix A — Smoke Suite Quick Reference

Appendix B — Defect Priority Decision Matrix

Appendix C — Effort Summary

Appendix D — Glossary

## 1. Introduction

### 1.1 Purpose

This Test Plan defines the complete testing strategy, scope, approach, and execution framework for OrangeHRM Version 5.0. It is the single governing reference for all QA activities conducted during the project lifecycle.

This document answers:

**What** will be tested (Scope)?

**How** will it be tested (Strategy & Approach)?

**Who** will test it (Resources)?

**When** will it happen (Schedule)?

**What** constitutes "done" (Exit & Closure Criteria)?

**How** will quality be measured (Metrics & KPIs)?

**Who** needs to know what and when (Communication Plan)?

### 1.2 Intended Audience

| Stakeholder | Role |
| --- | --- |
| QA Team | Primary execution of test cases |
| QA Lead | Review, metrics tracking, sign-off |
| Project Manager | Timeline and milestone oversight |
| Business Analysts | Requirement clarification, UAT coordination, TC sign-off |
| Development Team | Defect fix, environment setup, build deployment |
| Product Owner / Client | UAT approval and final production go/no-go sign-off |

### 1.3 Reference Documents

| Document | Version |
| --- | --- |
| OrangeHRM User Guide | 2.5 |
| OrangeHRM FSD v1.0 | 1.0 |
| OrangeHRM Test Cases (Excel) | v3.0 |
| OrangeHRM Test Cases (Markdown) | v3.0 |
| OWASP Testing Guide | v4.2 |
| Project Test Plan v1.0 (previous) | 1.0 |

## 2. Project Overview

OrangeHRM is an open-source Human Resource Management System. This engagement covers the publicly accessible demo environment.

Application URL: https://opensource-demo.orangehrmlive.com/web/index.php/auth/login

| Module | Primary Roles |
| --- | --- |
| Login / Logout / Password | All Users |
| Admin | Admin |
| PIM – Personnel Information | Admin, Supervisor, ESS |
| Leave Management | Admin, Supervisor, ESS |
| Time & Attendance | Admin, Supervisor, ESS |
| Dashboard & Directory | All Users |

Roles Under Test:

| Role | Access Level |
| --- | --- |
| Admin | Full system control |
| ESS (Employee Self-Service) | Own data only |
| Supervisor | Team data + approvals |

## 3. Test Objectives

**Functional Coverage** — Verify every feature under positive and negative conditions per the FSD.

**Security Validation** — Confirm protection against OWASP Top 10 basics: SQLi, XSS, IDOR, broken session management, sensitive data exposure.

**Role-Based Access Control** — Each role accesses only authorized modules and data.

**Workflow Integrity** — End-to-end business workflows function correctly (Leave Apply → Approve → Balance Update → Calendar).

**Data Integrity** — All CRUD operations maintain consistency. No data loss or corruption.

**Regression Assurance** — Defect fixes do not break existing functionality.

**Traceability** — Every TC maps to an identifiable requirement (TS_001–TS_006).

**Cross-Browser Verification** — Core flows validated in Chrome (primary) and Firefox (secondary).

## 4. Scope of Testing

### 4.1 In-Scope

| Module | Coverage |
| --- | --- |
| Login / Logout / Password | Valid login, invalid credentials, password masking, case sensitivity, forgot password, session expiry, SQL injection, URL password leak, back-button attack, change password (3 scenarios) |
| Admin | User CRUD, bulk delete, duplicate prevention, min-length validation, access restriction, XSS, password reset, SMTP config, Job Title/Location/Pay Grade config, custom user group privilege enforcement |
| PIM | Add employee, mandatory validation, duplicate ID, photo upload limits, edit personal + contact details, emergency contact, dependants, immigration, termination, financial data isolation, IDOR attack, search filters |
| Leave | Full-day and half-day apply, balance exhaustion, holiday exclusion, weekend date, past date, reverse date range, overlap prevention, approve, reject (balance restore), cancel pending, cancel approved, entitlement assign, calendar display |
| Time | Timesheet submission, 24h boundary, empty activity, read-only lock, supervisor approval, punch-in/out context, personal attendance records, project reports |
| Dashboard | Widget render, leave counter accuracy, directory sync, quick launch routing, ESS vs Admin widget differentiation |
| Cross-Browser | Full 7-TC Smoke Suite re-executed in Firefox |

### 4.2 Out of Scope

| Feature | Reason |
| --- | --- |
| Performance / Load Testing | Separate tooling (JMeter) — Phase 2 Non-Functional Test Plan |
| Mobile Native App | No native mobile app in scope |
| Payroll / Benefits Module | Not available in demo environment |
| Recruitment / Training Module | Outside current sprint boundaries |
| Full Test Automation | Planned for Phase 2 automation framework |
| Database-layer direct validation | Black-box approach — UI output assumed correct if DB functions |
| Localization / Multi-language | English-only; i18n testing deferred |

## 5. Assumptions

The following assumptions underpin this Test Plan. Any deviation must be logged as a risk:

The demo environment closely mirrors a production OrangeHRM 5.0 deployment behavior.

Business Analysts will respond to requirement queries within **1 business day**.

No major requirement changes will occur after test cases are signed off.

Defect fixes will not require changes to already-approved test cases (unless scope changes are formally agreed).

The Development Team will notify the QA team at least **2 hours before** any new build deployment to the QA environment.

All testers have received an orientation on OrangeHRM's domain context (HR workflows, leave cycles, timesheet cycles).

Test data preloaded in the demo environment will not be externally modified by other parties during active test cycles.

The demo environment's SMTP is either configured for testing OR the SMTP TC will be marked as Blocked with justification.

## 6. Dependencies

The QA team is blocked or constrained by the following external dependencies:

| # | Dependency | Owner | Impact if Delayed |
| --- | --- | --- | --- |
| D1 | Stable build deployed to QA environment | Development Team | Cannot begin Smoke or Functional testing |
| D2 | FSD v1.0 finalized and BA sign-off received | Business Analyst | TCs may not reflect correct requirements |
| D3 | All test accounts created and accessible | Dev / Environment Team | Cannot execute role-based TCs |
| D4 | Test data preloaded per module setup sections | Dev / Environment Team | TCs will fail on setup, not on functionality |
| D5 | Sprint dates and milestones confirmed by PM | Project Manager | Schedule cannot be finalized |
| D6 | SMTP credentials provided for email config test | Admin / IT Team | TC_ADM_09 marked Blocked |
| D7 | BA review + sign-off on all 75 TCs | Business Analyst | Cannot begin Cycle 1 formal execution |

## 7. Test Strategy

### 7.1 Approach

Testing follows a risk-based, black-box approach:

**Priority-first execution** — High priority TCs run first in every cycle.

**Role rotation** — Key flows tested under Admin, ESS, and Supervisor roles.

**Exploratory session** — 1 hour of unscripted exploratory testing per module before formal execution.

**Regression on fix** — Every defect fix triggers re-execution of the linked TC + impacted module Smoke TCs.

### 7.2 Test Design Techniques

| Technique | Applied To |
| --- | --- |
| Equivalence Partitioning | Login credentials, leave days, file sizes |
| Boundary Value Analysis | Username length (4, 5, 255, 256 chars), hours (0, 8, 24, 25), leave days (0, 1, balance-exact) |
| Decision Table Testing | Leave workflow (Apply → Approve / Reject / Cancel combinations) |
| State Transition Testing | Leave Status (Pending → Approved / Rejected → Cancelled), Timesheet (Draft → Submitted → Approved / Rejected) |
| Error Guessing | SQL Injection in login, XSS in name fields, blank mandatory fields, IDOR URL manipulation |
| Role-Based Matrix Testing | Each feature verified under all applicable roles |

### 7.3 Regression Strategy

Full Regression (all 75 TCs) is triggered when:

A major new build is deployed (> 3 modules changed)

More than 3 P1 defects are resolved in a single fix batch

Any core workflow (Login, Leave, Timesheet) is modified

Partial Regression (Smoke Suite + impacted module TCs) is triggered when:

An isolated bug fix targets a single module

A cosmetic / UI-only change is deployed

A single field-level validation is updated

Smoke Suite (14 TCs — marked Smoke Suite: Y) must pass before ANY other testing resumes after a new build.

Adding new TCs to Regression Suite: Any TC that was previously a Fail and is now re-verified as Pass is automatically promoted to the regression suite for future cycles. QA Lead approves additions.

### 7.4 Independence Principle

QA team will NOT receive pre-briefings from Development about which defects are "already fixed" before test execution. This ensures unbiased, independent verification.

## 8. Test Levels & Types

| Level | Description | TC Count | Owner |
| --- | --- | --- | --- |
| Smoke Testing | 14 critical TCs — Login, Add Employee, Apply Leave, Approve Leave, Submit Timesheet, Dashboard Load, Logout — in Chrome + Firefox | 14 | QA Team |
| Functional Testing | Module-by-module positive + negative coverage | 49 | QA Team |
| Security Testing | SQLi, XSS, IDOR, session timeout, URL bypass, password in URL, financial data isolation | 11 | QA Lead |
| Regression Testing | Smoke suite + impacted module TCs post defect fix | ~20 | QA Team |
| UAT | Business stakeholder validates 10 key workflows | 10 | Product Owner + BA |

## 9. Entry & Exit Criteria

### 9.1 Entry Criteria

| # | Gate |
| --- | --- |
| 1 | Application deployed to QA environment and accessible via URL |
| 2 | All 14 Smoke TCs pass (Y in Smoke Suite column = Pass) |
| 3 | All test accounts active: Admin, jdoe_ess, sup_test |
| 4 | Test data preloaded per all module setup sections |
| 5 | Test cases reviewed and signed off by Business Analyst |
| 6 | Defect tracking Excel workbook set up and shared |
| 7 | All testers have credentials and environment access |
| 8 | QA Lead has confirmed sprint start date with PM |

### 9.2 Exit Criteria

| # | Condition |
| --- | --- |
| 1 | 100% of Smoke Suite TCs = Pass |
| 2 | ≥ 95% of all 75 TCs executed |
| 3 | ≥ 95% pass rate on executed TCs |
| 4 | Zero open Critical (P0) defects |
| 5 | Zero open High (P1) defects |
| 6 | All Medium (P2) defects documented and accepted by Product Owner |
| 7 | Regression cycle completed — no new P0/P1 defects introduced by fixes |
| 8 | UAT sign-off email received from Product Owner |
| 9 | Test Summary Report delivered and approved by QA Lead |

### 9.3 Suspension Criteria

Suspend if:

Environment unavailable > 4 hours

A P0 blocker prevents > 30% of TCs from executing

New build deployed mid-cycle without prior QA notification

Resume when:

Environment confirmed stable — Smoke Suite passes

P0 blocker fixed, deployed, and verified by QA

New build passes full Smoke Suite

## 10. Test Closure Criteria

Test closure is formally declared when ALL of the following are satisfied:

| # | Condition |
| --- | --- |
| 1 | All test deliverables submitted and acknowledged by PM |
| 2 | Test Summary Report approved by QA Lead and PM |
| 3 | All defects dispositioned: Closed, Deferred (PO-approved), or Rejected |
| 4 | UAT sign-off document received and filed |
| 5 | Lessons Learned session conducted and notes shared with team |
| 6 | Test data and environment cleanup completed |
| 7 | Final QA sign-off email sent by QA Lead to all stakeholders |
| 8 | Test case archive (Excel + Markdown) backed up to project folder |

## 11. Test Metrics & KPIs

The following metrics will be tracked and reported daily during execution and weekly to stakeholders:

### 11.1 Execution Metrics

| Metric | Formula | Target |
| --- | --- | --- |
| TC Execution Rate | (Executed TCs / Total TCs) × 100 | ≥ 95% |
| TC Pass Rate | (Passed TCs / Executed TCs) × 100 | ≥ 95% |
| TC Fail Rate | (Failed TCs / Executed TCs) × 100 | ≤ 5% |
| Blocked TC Rate | (Blocked TCs / Total TCs) × 100 | ≤ 3% |

### 11.2 Defect Metrics

| Metric | Formula | Target |
| --- | --- | --- |
| Defect Density | Total Defects / Total TCs | < 0.3 (< 23 defects for 75 TCs) |
| P0/P1 Rate | (P0 + P1 Defects / Total Defects) × 100 | < 20% |
| Defect Fix Rate | Fixed Defects / Total Open Defects × 100 | ≥ 80% per cycle |
| Defect Reopen Rate | Reopened Defects / Total Fixed × 100 | < 10% |
| Defect Leakage | Bugs found in UAT / Total bugs found | < 5% |

### 11.3 Coverage Metrics

| Metric | Current Value |
| --- | --- |
| Total Requirements (Scenarios) | 6 (TS_001–TS_006) |
| Total Test Cases | 75 |
| Requirements Coverage | 100% (all TS IDs have TCs mapped) |
| Security Coverage | 11 Security TCs (14.7% of total suite) |
| Cross-Browser Coverage | 7 Smoke TCs × 2 browsers = 14 browser-specific runs |

## 12. Communication Plan

### 12.1 Daily Reporting

| What | Who Sends | To Whom | Channel | When |
| --- | --- | --- | --- | --- |
| Daily TC Execution Status | QA Lead | PM, BA, Dev Lead | Email + Excel attachment | End of each testing day (5:30 PM) |
| P0/P1 Defect Alert | QA Engineer (who finds it) | QA Lead + Dev Lead + PM | Instant message (chat) + Email | Within 30 minutes of discovery |
| Build Deployment Notice | Dev Lead | QA Lead | Email / Chat | Minimum 2 hours before deployment |
| Defect Fix Ready Notification | Developer | QA Lead | Defect tracking sheet update + Email | After deploying fix to QA environment |

### 12.2 Weekly Reporting

| What | Who Sends | To Whom | Channel | When |
| --- | --- | --- | --- | --- |
| Weekly Test Progress Report | QA Lead | PM + Stakeholders + BA | Email with Excel dashboard | Every Friday by 4:00 PM |
| Defect Triage Meeting | QA Lead (facilitates) | Dev Lead, BA, QA Team | Video call (30 min) | Every Tuesday, 10:00 AM |

### 12.3 Milestone Reporting

| Milestone | Report | Audience |
| --- | --- | --- |
| Smoke Testing Complete | Smoke Pass/Fail Summary | PM, Dev Lead, QA Lead |
| Cycle 1 Execution Complete | Cycle 1 Execution Report | All stakeholders |
| UAT Complete | UAT Sign-off Document | PM, Product Owner |
| QA Closure | Test Summary Report | All stakeholders |

### 12.4 Escalation Path

Tester → QA Lead (within same day)
QA Lead → Project Manager (if P0 unresolved > 24hrs or environment down > 4hrs)
Project Manager → Client / Product Owner (if schedule or scope is impacted)

## 13. Test Environment

### 13.1 Application Details

| Property | Value |
| --- | --- |
| Application | OrangeHRM Version 5.0 |
| Environment Type | Demo / QA |
| URL | `https://opensource-demo.orangehrmlive.com/web/index.php/auth/login` |
| Environment Owner | Development Team |

### 13.2 Test Accounts

| Role | Username | Password | Mapped Employee |
| --- | --- | --- | --- |
| Admin | `Admin` | `admin123` | System Admin |
| ESS User | `jdoe_ess` | `Test@1234` | John Doe |
| Supervisor | `sup_test` | `Sup@1234` | Jane Smith |
| Secondary Admin | `admin_secondary` | `SecAdmin@1` | N/A |

### 13.3 Browser & OS Compatibility Matrix

| Browser | OS | Version | Priority | Scope |
| --- | --- | --- | --- | --- |
| Chrome | Windows 11 | 118.x | P0 — Primary | Full 75 TCs |
| Chrome | macOS Ventura | 118.x | P1 | Smoke only |
| Firefox | Windows 11 | 118.x | P1 | 7-TC Smoke Suite |
| Safari | macOS / iOS 16 | 16.x | P1 | Smoke only |
| Edge | Windows 11 | 118.x | P2 | Smoke only |

### 13.4 Device & Resolution Scope

| Device | Resolution | Scope |
| --- | --- | --- |
| Desktop | 1920 × 1080 | Full 75 TCs |
| Laptop | 1366 × 768 | Functional (48 TCs) |
| Tablet | 768 × 1024 | Smoke only (14 TCs) |
| Mobile | 375 × 812 | Smoke only — critical ESS flows |

## 14. Test Data Requirements

| Module | Required Data |
| --- | --- |
| Login | Admin, ESS, Supervisor accounts — unlocked; Admin email configured |
| Admin | `admin_secondary`, `test_u1/u2/u3`; Job Title `QA Engineer`; Location `HQ` |
| PIM | `Alice Smith` (EMP#0001); `Bob Test` with ESS login; EMP#0002 exists (for duplicate ID TC); Sub-Units and Employment Statuses configured |
| Leave | John Doe: Annual=10, Sick=1 (0 taken); Holiday Dec 25=Christmas; Leave types: Annual, Sick; Weekends=non-working |
| Time | Project `Alpha` (Activity: `Development`); Project `Beta` (no activities); `jdoe_ess` assigned to Alpha; current week = Not Submitted; prior week = Submitted |
| Dashboard | 1 pending leave under Supervisor team; `New Employee` added in PIM just before TC_DSH_03 |

Data Reset Policy: Full reset at start of each cycle.

Responsibility: Development / Environment Team prepares; QA Lead validates before execution starts.

## 15. Test Deliverables

| Deliverable | Owner | Due |
| --- | --- | --- |
| Test Plan v2.0 (this document) | QA Lead | Sprint Day 1 |
| Test Cases v3.0 (Excel + Markdown) | QA Team | Sprint Day 2 |
| RTM (embedded in Test Cases) | QA Team | Sprint Day 2 |
| Defect Tracking Workbook (Excel) | QA Lead | Sprint Day 1 |
| Cycle 1 Execution Report | QA Team | End of Sprint Day 7 |
| Regression Test Report | QA Team | End of Sprint Day 11 |
| Security Test Report | QA Lead | Sprint Day 11 |
| UAT Test Scripts | QA Team | Sprint Day 12 |
| Test Summary Report | QA Lead | Sprint Day 14 |
| Lessons Learned Notes | QA Lead | Sprint Day 14 |

## 16. Defect Management

### 16.1 Severity & SLA

| Severity | Definition | Fix SLA |
| --- | --- | --- |
| **Critical (P0)** | System crash, data loss, security breach, cannot login, core feature unusable | < 24 hours |
| **High (P1)** | Major feature broken, significant workflow blocked | < 48 hours |
| **Medium (P2)** | Partially working, clear workaround exists | 3–5 business days |
| **Low (P3)** | Cosmetic, minor text, UI misalignment | Next release |

### 16.2 Defect Lifecycle

New → Open → In Progress → Fixed/Resolved → Verified
                                          ↘ Reopened (if fix fails) → In Progress
                        ↘ Deferred / Rejected (requires Product Owner approval)
                    Verified + Pass → Closed

### 16.3 Defect Report Template

| Field | Description |
| --- | --- |
| Bug ID | Auto-generated |
| Module | e.g., Leave, Admin, PIM |
| Req. ID | e.g., TS_004 |
| Linked TC ID | e.g., TC_LEV_03 |
| Summary | [Action] causes [Error] when [Condition] |
| Pre-requisites | System state before test |
| Steps to Reproduce | Numbered, step-by-step |
| Expected Result | Copied from TC's ER column |
| Actual Result | Observed behavior |
| Severity / Priority | e.g., High / P1 |
| Environment | Browser + OS + Resolution |
| Build Version | e.g., 5.0.1 |
| Attachments | Screenshot.png / Recording.mp4 |
| Reported By | Tester name |
| Date Reported | Date |

### 16.4 Tool

All defects tracked in Microsoft Excel (Defect Tracking Workbook), linked to TC IDs. Defect ID column populated in the TC execution sheet against each failed TC.

## 17. Risk & Mitigation Plan

| # | Risk | Prob % | Impact | Risk Score | Mitigation |
| --- | --- | --- | --- | --- | --- |
| R1 | Demo environment reset/unavailable | 70% | High (3) | 2.1 | Execute tests in sessions; screenshot all evidence; re-create data via Module Setup scripts |
| R2 | Test data wiped between sessions (shared demo) | 65% | High (3) | 1.95 | Re-run Module Setup before each session; use a dedicated test data prep checklist |
| R3 | Requirements ambiguity leads to wrong TCs | 25% | Medium (2) | 0.5 | BA reviews and signs off all 75 TCs before execution; clarification tracker maintained |
| R4 | Defect backlog grows faster than fix rate | 40% | High (3) | 1.2 | Daily defect triage meeting (Tuesdays); P0/P1 fixed within SLA; defer P3 to next release |
| R5 | UAT/FE changes between builds invalidate TCs | 35% | Medium (2) | 0.7 | Flag as Blocked; update TC only after BA confirms scope change |
| R6 | Security scenarios are skipped under time pressure | 20% | High (3) | 0.6 | QA Lead owns all 11 security TCs; they are scheduled on Day 10 as a locked session |
| R7 | Key tester unavailability | 20% | Medium (2) | 0.4 | Cross-train 2 testers per module; progress log updated daily |
| R8 | SMTP unavailable for email TC | 50% | Low (1) | 0.5 | Mark TC_ADM_09 as Blocked with justification; test SMTP in staging using a mock server |

Risk Score = (Probability % / 100) × Impact (1=Low, 2=Med, 3=High)

Threshold: Risk Score > 1.5 = Escalate to PM

## 18. Resource Plan

| Role | Responsibility | Allocation |
| --- | --- | --- |
| QA Lead | Test Plan authoring, TC review, all 11 security TCs, Metrics tracking, sign-off, Lessons Learned | 100% |
| QA Engineer 1 | Login, Admin, PIM module TCs execution | 100% |
| QA Engineer 2 | Leave, Time, Dashboard module TCs execution + Cross-browser Smoke | 100% |
| Business Analyst | Requirement clarification, TC review + sign-off, UAT coordination | 20% |
| Developer | Defect fix, environment setup, build deployment, data prep support | As needed |
| Product Owner | UAT execution, go/no-go sign-off | 10% |

## 19. Test Schedule & Milestones

| Phase | Duration | Key Activities | Effort | Deliverable |
| --- | --- | --- | --- | --- |
| 1. Planning & Setup | Days 1–2 | Test Plan finalization, TC BA review, account + data setup validation | 8 hrs | Signed-off Test Plan + TC; Test data ready |
| 2. Smoke Testing | Day 3 | Execute 14 Smoke TCs (Chrome + Firefox) | 4 hrs | Smoke Pass/Fail Summary |
| 3. Functional Testing (Cycle 1) | Days 3–7 | Execute all 75 TCs; log defects; exploratory session per module | 40 hrs | Cycle 1 Execution Report; Defect Dump |
| 4. Defect Triage | Day 8 | Daily triage meeting; Dev fixes P0/P1; QA validates blockers | 4 hrs | Confirmed fix list |
| 5. Security Testing | Days 9–10 | Execute 11 security TCs; document findings | 6 hrs | Security Test Report |
| 6. Regression (Cycle 2) | Days 10–11 | Re-run failed TCs + full Smoke Suite post fixes | 12 hrs | Regression Report; Zero P0/P1 achieved |
| 7. UAT | Days 12–13 | Business stakeholders execute 10 key workflows; QA supports | 8 hrs | UAT Sign-off Email |
| 8. Closure | Day 14 | Test Summary Report; Lessons Learned; archive; sign-off email | 4 hrs | Test Summary Report; Release Recommendation |
| **Total** | **14 days** |  | **86 hrs** |  |

Dates will be adjusted per actual project start date. All phasing assumes 2 QA Engineers + 1 QA Lead working in parallel.

## 20. Requirements Traceability Matrix (RTM)

| Req. / Scenario ID | Module | Feature Description | TC IDs | TC Count |
| --- | --- | --- | --- | --- |
| TS_001 | Login | Login, Logout, Password, Session, Security | TC_LOG_01 to TC_LOG_14 | 14 |
| TS_002 | Admin | User CRUD, Job/Org config, Access Control, XSS | TC_ADM_01 to TC_ADM_13 | 13 |
| TS_003 | PIM | Employee CRUD, Tabs, Role Access, IDOR, Termination | TC_PIM_01 to TC_PIM_13 | 13 |
| TS_004 | Leave | Apply, Approve, Reject, Cancel, Entitlement, Calendar | TC_LEV_01 to TC_LEV_14 | 14 |
| TS_005 | Time | Timesheets, Attendance, Reports | TC_TIM_01 to TC_TIM_08 | 8 |
| TS_006 | Dashboard | Widgets, Directory, Quick Launch, ESS vs Admin | TC_DSH_01 to TC_DSH_06 | 6 |
| TS_006 (ext) | Cross-Browser | Firefox Smoke parity | TC_FF_01 to TC_FF_07 | 7 |
| **TOTAL** |  |  |  | **75** |

### Coverage Summary

| Test Type | TC Count | % of Total |
| --- | --- | --- |
| Smoke | 14 | 18.7% |
| Functional | 49 | 65.3% |
| Security | 11 | 14.7% |
| Regression | 1 | 1.3% |
| **Total** | **75** | **100%** |

## Appendix A — Smoke Suite Quick Reference

Execute these 14 TCs FIRST on every new build. All must Pass before full execution begins.

| TC ID | Module | Title | ER Summary |
| --- | --- | --- | --- |
| TC_LOG_01 | Login | Login with valid Admin credentials | Redirected to Dashboard |
| TC_LOG_06 | Login | Successful logout | Redirected to Login page; session cleared |
| TC_PIM_01 | PIM | Add new employee | Saved; redirects to Personal Details |
| TC_LEV_01 | Leave | Apply full-day leave | Saved; Status = Pending Approval |
| TC_LEV_09 | Leave | Supervisor approves leave | Status = Approved; Calendar updated |
| TC_TIM_01 | Time | Submit 40-hour timesheet | Status = Submitted; Supervisor notified |
| TC_DSH_01 | Dashboard | All widgets render correctly | No errors, no stuck spinners |
| TC_FF_01 | Cross-Browser | [Firefox] Login | Same as TC_LOG_01 |
| TC_FF_02 | Cross-Browser | [Firefox] Logout | Same as TC_LOG_06 |
| TC_FF_03 | Cross-Browser | [Firefox] Add Employee | Same as TC_PIM_01 |
| TC_FF_04 | Cross-Browser | [Firefox] Apply Leave | Same as TC_LEV_01 |
| TC_FF_05 | Cross-Browser | [Firefox] Approve Leave | Same as TC_LEV_09 |
| TC_FF_06 | Cross-Browser | [Firefox] Submit Timesheet | Same as TC_TIM_01 |
| TC_FF_07 | Cross-Browser | [Firefox] Dashboard Loads | Same as TC_DSH_01 |

## Appendix B — Defect Priority Decision Matrix

Use this 2×2 grid to eliminate subjectivity when assigning Priority to defects:

|  | **High Business Impact** | **Low Business Impact** |
| --- | --- | --- |
| **Critical/High Severity** | **P0 — Showstopper**: Fix immediately. Block release. | **P1 — Urgent**: Fix in current build. |
| **Medium/Low Severity** | **P2 — Normal**: Fix before release candidate. | **P3 — Low**: Defer if time constrained; fix in next version. |

Examples:

Cannot login → Critical Severity + High Business Impact = **P0**

Leave balance shows wrong number → High Severity + High Business Impact = **P0/P1**

UI misalignment on Admin page → Low Severity + Low Business Impact = **P3**

Search filter missing one valid result → Medium Severity + High Business Impact = **P2**

## Appendix C — Effort Summary

| Role | Phase 1 | Smoke | Functional | Security | Regression | UAT | Closure | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| QA Lead | 4 hrs | 1 hr | 8 hrs | 6 hrs | 4 hrs | 4 hrs | 4 hrs | **31 hrs** |
| QA Engineer 1 | 2 hrs | 1.5 hrs | 20 hrs | 0 | 4 hrs | 2 hrs | 0 | **29.5 hrs** |
| QA Engineer 2 | 2 hrs | 1.5 hrs | 20 hrs | 0 | 4 hrs | 2 hrs | 0 | **29.5 hrs** |
| **Total** | **8 hrs** | **4 hrs** | **48 hrs** | **6 hrs** | **12 hrs** | **8 hrs** | **4 hrs** | **90 hrs** |

## Appendix D — Glossary

| Term | Definition |
| --- | --- |
| TC | Test Case |
| TS | Test Scenario (parent grouping of TCs) |
| ER | Expected Result |
| QA | Quality Assurance |
| UAT | User Acceptance Testing |
| ESS | Employee Self-Service (OrangeHRM role) |
| PIM | Personnel Information Module |
| CRUD | Create, Read, Update, Delete |
| RTM | Requirements Traceability Matrix |
| SLA | Service Level Agreement (defect fix turnaround) |
| P0/P1 | Critical / High priority defects |
| XSS | Cross-Site Scripting (OWASP security vulnerability) |
| SQLi | SQL Injection (OWASP security vulnerability) |
| IDOR | Insecure Direct Object Reference — accessing other users' data by modifying IDs in URLs |
| CSRF | Cross-Site Request Forgery |
| SMTP | Simple Mail Transfer Protocol (email server config) |
| HRIS | Human Resource Information System |
| Entitlement | Allocated leave days assigned to an employee for a period |
| Timesheet Cycle | A weekly period during which employees log worked hours |

Document: OrangeHRM Test Plan v2.0 | Maturity Target: Level 4 (Managed)

Covers 75 Test Cases | 7 Modules | 6 New Sections vs v1.0